## Sheet1
Test Plan and Result Template
Project Name | Adaptive Gyro Controller
Engineer | Landen Barber
Test Plan Date and update dates | Created: 4/4/2026 | Updated: 5/18/26, 5/25/26, 5/26/26, 5/27/26
Requir+B4+A5:F6+A5:C6+A5+A5:F6 | Requirement Number2 | Requirement Description | Percent Complete | Test methodology | Test Equipment | Special test condition | Test Disposition | Test Date | Test Trial No. | Associated test document | Test Notes
Design? Functionalities? Performance? | Requirement Number from requirements doc. | Succintly desribe your requirement. If original requirement is too big, you can break down into multiple rows. | List pct complete | How was this requirement tested? Press ALT+ENTER for new line in Excel | List any test equipment used for the test | List any special conditions for your test | PASS, FAIL, PARTIAL PASS | List the planned date or run | List number of test attempts | List associated test documents here by file name indicating proof of successful test. Place the documents into the same folder as this template | You can make a memo of your observation or follow-up actions needed. You should make a separate table if you tried multiple times. The multiple trials are really key food for your evaluation section.
| 1 | ICM-20948 | 75% |  |  |  | PARTIAL PASS |  |  |  | Partial Pass for now as more testing is required after PCB and 3d models are done.
| 1.1 | Read from WHO_AM_I register | 100% | Expected value 0xEA |  |  | PASS | 2026-05-25 | 1 | Module returns 0xEA signifying it is set up correctly and outputting data | Returns 0xEA meaning that device is set up and outputting data.
| 1.2 | Read Gyroscope values | 60% | Expected range: +-250dps - +-2000dps, get min and max values by moving as fast as possible and finding how quick it needs to be to activate a difference |  |  | PARTIAL PASS | 2026-05-25 | 2 |  | Feels like gyro is giving weird values, hard to test until the mounting parts arrive.
| 1.3 | Read accelerometer values | 75% | Expected range: +-2g – +-16g [1] |  |  | PARTIAL PASS | 2026-05-25 | 2 |  | Also hard to test definitively until parts arrive.
| 1.4 | Read Magnetometer values | 70% | Expected wide range of +-4900uT [1] Uses separate chip, WHO_AM_I should return 0x4809 |  |  | PARTIAL PASS | 2026-05-25 | 2 |  | Also hard to test definitively until parts arrive.
| 2 | ADC / DMA Testing | 100% |  |  |  | PASS
| 2.1 | ADC / DMA Starting without critical errors | 100% | HAL_ADC_Start_DMA() should return HAL_OK on completion |  |  | PASS | 2026-05-25 | 1 | Returned HAL_OK on initialization
| 2.2 | Read Joystick values at neutral position (expected value ~2048) | 100% | 12bit ADC (0-4095) [2] Neutral value expected to be 2048 +- 100 |  |  | PASS | 2026-05-25 | 1 | J1: X: 2044 – 2049 Y: 2098 – 2101 J2: X: 2031 – 2037 Y: 2033 – 2039
| 2.3 | Check all directions of each joystick | 100% | Full range: min = 0-50 to max 4045-4095 depending on direction <10ms per axis update |  |  | PASS | 2026-05-25 | 1 | Joysticks measured full range of motion
| 2.4 | Check both Joysticks | 100% | Verify ADC is placing data in correct spots. |  |  | PASS | 2026-05-25 | 1 | Data is being placed in correct lotions, tested with two different clock speeds
| 3 | Powerboost 1000c Battery USB-C Charging | 100% |  |  |  | PASS
| 3.1 | Boost Output voltage from battery | 100% | Measuring GND and 5v pin with multimeter ~5.2v [3] | Multimeter |  | PASS | 2026-05-25 | 1 | Multimeter reads 5.14v under load with charged battery.
| 3.2 | Boost Output voltage while charging | 100% | Measuring GND and 5v pin with multimeter ~5.2v [3] Charge current 1000mA max | Multimeter |  | PASS | 2026-05-25 | 1 | Multimeter reads 5.16v while battery charging and under load
| 3.3 | Normal Output from Battery | 100% | Measuring GND and 5v pin with multimeter ~3.3v [4] | Multimeter |  | PASS | 2026-05-25 | 1 | Multimeter reads 3.61v from battery.
| 3.4 | Normal Output while charging | 100% | Measuring GND and 5v pin with multimeter ~3.3v [4] | Multimeter |  | PASS | 2026-05-25 | 1 | Multimeter reads 4.56v from battery while charging.
| 3.5 | No power outage when switching load source | 100% | Seamless transition because of load sharing circuit [3] | Multimeter |  | PASS | 2026-05-25 | 1 | Plugging in and unplugging charging cable does not interrupt program operation.
| 3.6 | Output voltage at max load | 100% | Max 1000mA of continuous draw [3] Stays above 5v when low charge [3] | Multimeter |  | PASS | 2026-05-25 | 1 | Automatically shuts off when falling below ~5.02v (Last checked num)
| 3.7 | Low battery voltage cutoff | 100% | Red LED lights up at low charge (battery outputting below 3.2v) Boost converter cuts off below 3v | Multimeter |  | PASS | 2026-05-25 | 1 | Red light on power boost works, currently no ADC can take in voltage.
| 4 | Bluetooth Low Energy | 10% |  |  |  | PARTIAL PASS |  |  |  | Needs to be redone in a new project. Doesn’t quite work with other features currently.
| 4.1 | Enter pairing mode when holding button (resetting) | 50% |  |  |  | PARTIAL PASS | 2026-05-26 | 3 |  | Easy enough, waiting for other features to work correctly.
| 4.2 | Pair with windows PC | 25% |  |  |  | PARTIAL PASS | 2026-05-26 | 3 |  | Will work when project rebuilt with HID profile.
| 4.3 | auto reconnect with last paired device when powered on or disconnected | 25% |  |  |  | PARTIAL PASS | 2026-05-26 | 3 |  | Should be included in most BLE libraries already.
| 5 | Buttons Testing | 100% |  |  |  | PASS
| 5.1 | All buttons working | 100% | Low: connect to GND (0v) Release: pin reads High (~3.3v) |  |  | PASS | 2026-05-25 | 1
| 5.2 | Button debouncing working | 100% | Debounce delay: 20ms Single press activates single button, no multiple counts |  |  | PASS | 2026-05-25 | 1
| 6 | Haptic Motor | 100% |  |  |  | PASS
| 6.1 | Haptic motors working at different strengths | 100% | PWM at 150Hz to 250Hz |  |  | NA | 2026-05-25 | 1
| 6.2 | Haptic motors differentiated | 100% | Motors can be controlled independently or simultaneously Non-blocking program |  |  | PASS | 2026-05-25 | 1 | They can be controlled independently, not blocking.
| 7 | Battery indicator LED and voltage detection | 80% |  |  |  | PARTIAL PASS |  |  |  | LED working fine without blocking, will need to split power input into an adc input, need to figure out how to add another adc usage that doesn’t get added to a register along joystick inputs when I have time.
| 7.1 | LED working | 100% | 3.3v High (White light) |  |  | PASS | 2026-05-25 | 1
| 7.2 | LED blinking at different speeds for voltage differences | 50% | Read battery voltage from ADC, Clamp to blinking speeds |  |  | NA | 2026-05-25 | 1
| 7.3 | LED blinking to signify BLE pairing mode | 75% | Fast blinking for pairing mode Successful pairing makes short pattern before writing battery voltage |  |  | PARTIAL PASS | 2026-05-25 | 1 |  | Theoretically working, need to work on BLE more.
| 8 | One handed symmetrical layout | 0% |  |  |  | NA |  |  |  | Waiting on parts to arrive.
| 8.1 | Turn on controller and test main features to make sure they are comfortable and usable with one hand | 0% | All buttons reachable |  |  | NA | 2026-06-01 | 1 |  | Waiting on parts to arrive.
| 8.2 | Use strap wave hand around to ensure stability | 0% | Accelerometer tracking rapid hand movements without loosening grip |  |  | NA | 2026-06-01 | 1 |  | Waiting on parts to arrive.
| 8.3 | Drop from heights to ensure durability | 0% | Drop from 1-2m onto carpet Drop .5m on hard floor |  |  | NA | 2026-06-01 | 1 |  | Waiting on parts to arrive.
| 9 | Gyro as Mouse Cursor | 75% |  |  |  | PARTIAL PASS
| 9.1 | Moving controller allows Cursor to follow | 60% | Rotation of 10 deg moves cursor 100-300 pixels (dependent on sensitivity) Response latency <30ms [2] |  |  | FAIL | 2026-06-01 | 1
| 9.2 | Small tilt (low sensitivity mode for precise movement) | 80% | Eliminate cursor jitter: when <5pixels at rest |  |  | PARTIAL PASS | 2026-05-25 | 1
| 9.3 | Large tilt (high sensitivity mode for fast movement) | 80% | < 60deg motion, maximum cursor speed > 2000 pixels/second |  |  | PARTIAL PASS | 2026-05-25 | 1
| 9.4 | Orientation pausing button working to allow readjustment | 100% | Freeze cursor movement while button is held. No abrupt cursor jumping after release. |  |  | PASS | 2026-05-25 | 1
| 10 | Gesture Recognition | 70% |  |  |  | PARTIAL PASS
| 10.1 | Quick swipe up/down/left/right to activate simple flick gesture | 70% | Angular velocity threshold >200deg/sec, min distance 15deg Aim to have 95% detection rate for intentional gestures |  |  | PARTIAL PASS | 2026-05-25 | 1
| 10.2 | Quick tilt left to activate simple gesture | 70% | 300ms detection window Recognize when a gesture fails to activate |  |  | PARTIAL PASS | 2026-05-25 | 1
| 10.3 | Slow movement for no gesture | 80% | If angular velocity <150deg/sec, gesture not triggered |  |  | PARTIAL PASS | 2026-05-25 | 1
| 10.4 | Adjustable threshold values | 100% | Highly adjustable thresholds for filter strength, gesture sensitivity(like 200-400deg/s to trigger), minimum distance threshold 30deg |  |  | PASS | 2026-05-25 | 1
| 11 | Adaptive Analyzer | 75% |  |  |  | PARTIAL PASS |  |  |  | Code mostly written, needs to be fine tuned to make it work better.
| 11.1 | User always flicks quickly, increase threshold | 80% | If 10 gestures with velocity > 400deg/s, increase threshold by 10-20% (check for min and max values) |  |  | PARTIAL PASS | 2026-05-26 | 1
| 11.2 | User flicks slowly, decrease threshold | 80% | After 10 gestures with velocity < 250deg/sec, decrease threshold by 10-20% You should acclimate to user in ~100 gestures. |  |  | PARTIAL PASS | 2026-05-26 | 1
| 11.3 | User fails to activate gesture, increase timing window | 70% | If three failures trigger a gesture within 60 sec, increase timing window 50-100ms. |  |  | PARTIAL PASS | 2026-05-26 | 1
| 11.4 | User is slow to activate gesture, decrease timing window | 70% | If failure to activate gestures within timing window happens over three times, decrease the timing window by 10-20% |  |  | PARTIAL PASS | 2026-05-26 | 1
| 11.5 | Settings persist after power off | 100% | Store vital settings in flash memory for quicker boot After power cycle, settings will be retained. |  |  | PASS | 2026-05-26 | 1
| 12 | Screen Overlay | 0% |  |  |  | NA |  |  |  | Unimplemented
| 12.1 | Open Overlay | 0% | Window appears in ~200ms after holding button |  |  | NA | 2026-05-25 | 1 |  | Unimplemented
| 12.2 | Close Overlay | 0% | Window closes within 100ms of closing press |  |  | NA | 2026-05-25 | 1 |  | Unimplemented
| 12.3 | Change gyro sensitivity or other settings | 0% |  |  |  | NA | 2026-05-25 | 1 |  | Unimplemented
| 12.4 | Save settings to controller storage | 100% | Save operation completes in less than 400ms Events can be saved in under 300ms |  |  | PASS | 2026-05-25 | 1
| 13 | Digital Keyboard | 0% |  |  |  | NA |  |  |  | Unimplemented
| 13.1 | Open digital keyboard on PC window | 0% | Keyboard opens within 300ms of pressing button. Window size adjustable, default could be 1000x500pixels in standard layout. |  |  | NA | 2026-05-25 | 1 |  | Unimplemented
| 13.2 | Pressing buttons emulates keyboard input | 0% | < 50ms latency from button press to make cursor click and type in key like keyboard. |  |  | NA | 2026-05-25 | 1 |  | Unimplemented
| 14 | Settings / Key bind Editor | 0% |  |  |  | NA |  |  |  | Unimplemented
| 14.1 | Open/Close setting editor on PC window | 0% | Editor opens in ~300ms Takes ~150ms to save to storage |  |  | NA | 2026-05-25 | 1 |  | Unimplemented
| 14.2 | Change settings using joystick or pc controls | 0% | Can use joystick/gyr controls or computer mouse to change settings if unusable with current settings. |  |  | NA | 2026-05-25 | 1 |  | Unimplemented
| 14.3 | Save settings to local storage | 100% | Save in a readable format that can be duplicated to make multiple profiles. |  |  | PASS | 2026-05-25 | 1
| 15 | Profile Management | 100% |  |  |  | PASS
| 15.1 | Create two profiles with different settings | 100% | Can switch between profiles without power cycling Takes less than 200ms to switch between profiles |  |  | PASS | 2026-05-26 | 1
| 15.2 | Switch between two profiles and test controller functionality to ensure settings are applied | 100% |  |  |  | PASS | 2026-05-26 | 1
| 15.3 | Load profile after power cycling | 100% | Default profile can be set to be loaded after powering on Boots in less than 750ms |  |  | PASS | 2026-05-26 | 1
| 15.4 | Delete a Profile | 0% | After deletion and confirmation, profile is removed from list and gives back storage. |  |  | NA | 2026-05-26 | 1